## Gantt Chart
click here to buy premium edition at excelindo.com
SETTING
| Start Date | : | 2017-08-01 |  |  | PROJECT NAME |  | Smart Mall Shopping
| End Date | : |  |  |  | DESCRIPTION
| End Date | TRUE | 2017-12-26
| Week Period | FALSE | 20 |  |  | LEADER |  | Bhagyashri Kamble
| Working Days | : | R Monday
|  |  | R Tuesday |  |  | u | Start Date | 2017-08-01 |  |  | End Date : | 2017-12-26
|  |  | R Wednesday |  |  | u | Project Length | 22 Week
|  |  | R Thursday |  |  | u | Week Period (52 Week) | W1 - W22 | 0
|  |  | R Friday |  |  |  |  | 7/31/17 - 12/31/17 | 2017-12-31
|  |  | Saturday | FALSE | 6 | [9 empty] | 2017-07-31 | 2017-09-04 | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
|  |  | Sunday | FALSE | 7 | Level | Task | Assignment |  |  | Start Date | Finish Date | Work Days | Remaining WD | W1 | [6 empty] | 1: W2; 8: W3; 15: W4; 22: W5 | [6 empty] | W6 | [6 empty] | W7 | [6 empty] | W8 | [6 empty] | W9 | [6 empty] | W10 | [6 empty] | W11 | [6 empty] | W12 | [6 empty] | W13 | [6 empty] | W14 | [6 empty] | W15 | [6 empty] | W16 | [6 empty] | W17 | [6 empty] | W18 | [6 empty] | W19 | [6 empty] | W20 | [6 empty] | W21 | [6 empty] | W22
| Today's Date | : | [12 empty] | 1899-12-31 | 2017-07-31 | [5 empty] | 1: 1900-01-01; 2: 2017-08-07; 8: 1900-01-02; 9: 2017-08-14; 15: 1900-01-03; 16: 2017-08-21; 22: 1900-01-04 | 2017-08-28 | [5 empty] | 1900-01-05 | 2017-09-04 | [5 empty] | 1900-01-06 | 2017-09-11 | [5 empty] | 1900-01-07 | 2017-09-18 | [5 empty] | 1900-01-08 | 2017-09-25 | [5 empty] | 1900-01-09 | 2017-10-02 | [5 empty] | 1900-01-10 | 2017-10-09 | [5 empty] | 1900-01-11 | 2017-10-16 | [5 empty] | 1900-01-12 | 2017-10-23 | [5 empty] | 1900-01-13 | 2017-10-30 | [5 empty] | 1900-01-14 | 2017-11-06 | [5 empty] | 1900-01-15 | 2017-11-13 | [5 empty] | 1900-01-16 | 2017-11-20 | [5 empty] | 1900-01-17 | 2017-11-27 | [5 empty] | 1900-01-18 | 2017-12-04 | [5 empty] | 1900-01-19 | 2017-12-11 | [5 empty] | 1900-01-20 | 2017-12-18 | [5 empty] | 1900-01-21 | 2017-12-25
| Actual | TRUE | 2017-09-05
| User Defined | FALSE | 2011-12-07
[5 empty] | 2017-09-05 | 0 | time axis 2017-07-31 to 2017-12-31
| Level Type | : | 1; 1.1; 1.1.1; .. | 0 |  | 1 | Project selection | Pragati Patil |  | 42983 | 2017-08-01 | 20/08/2017
| DAYS MARKER |  |  |  |  | 1.1 | Define project name | Pragati Patil |  | 0 | 2017-08-21 | 2017-08-22 | 2
| Today | : | Yes | 1 |  | 1.2 | Problem Statement |  |  | 0 | 2017-08-23 | 2017-08-24 | 2
| Holiday | : | No | 0 |  | 1.3 | SRS Document |  |  | 42983 | 2017-08-25 | 2017-09-15 | 16 | 9
| Leave | : | No |  |  | 1.4 | Front end Dedign for Teacher |  |  | 42994 | 2017-09-16 | 2017-09-21 | 4 | 4
| Start/End | : | No |  |  | 1.5 | Front end Dedign for blind person |  |  | 43000 | 2017-09-22 | 2017-09-27 | 4 | 4
| Passing Days | : | No | 0 |  | 1.6 | Front end Design for admin |  |  | 43006 | 2017-09-28 | 2017-09-30 | 2 | 2
| DISPLAY |  |  |  |  | 2 | Add functions into Teacher template |  |  | 43009 | 2017-10-01 | 2017-10-20 | 15 | 15
| Window | : | 52 Week | 4 |  | 2.1 | Add functions into admin template |  |  | 43029 | 2017-10-21 | 2017-10-31 | 7 | 7
| Slider | : | Weekly | 1 |  | 2.3 | Add functions into blind person template |  |  | 43040 | 2017-11-01 | 2017-11-10 | 8 | 8
| ALERT |  |  |  |  | 3 | link three templates |  |  | 43050 | 2017-11-11 | 2017-11-12 | 0 | 0
| Remaining Days | : | 0 |  |  | 3.1 | Check flow |  |  | 43052 | 2017-11-13 | 2017-11-16 | 4 | 4
[6 empty] | 3.2 | Give project to customer for demo |  |  | 43056 | 2017-11-17 | 2017-11-30 | 10 | 10
[6 empty] | 3.3 | Changes into project if require |  |  | 43070 | 2017-12-01 | 2017-12-25 | 17 | 17
© 2012 excelindo.com
more free templates at exceltemplate.net

## Holiday List
Date | Holiday
2012-01-01 | New Year’s Day
2012-01-16 | Martin Luther King, Jr. Day
2012-02-20 | Presidents’ Day
2012-05-28 | Memorial Day
2012-07-04 | Independence Day
2012-09-03 | Labor Day
2012-10-08 | Columbus Day
2012-11-11 | Veterans Day
2011-11-22 | Thanksgiving Day
2012-12-25 | Christmas Day

## Premium Edition Features
PRICE | Excelindo Gantt Chart Premium Edition - Single User License | US$ 17.99 | click here to buy premium edition at excelindo.com
| Excelindo Gantt Chart Premium Edition - Multi User License | US$ 34.99
EXCELINDO GANTT CHART PREMIUM EDITION FEATURES
Flexible Work Days
Some projects required different holidays instead of normal Saturday or Sunday. Using this flexible work days feature, users can select their own work days within one week.
Custom Holiday and Leave Dates
These features will allow users to add their company holidays and their personal leaves into the chart and being included in total workday calculation which will make the plan more precise.
Smart Workdays Calculation
Based on flexible workdays and custom holidays, the formula inside Workday column will calculate precisely users workdays.
Chart Marker
These are features that will colorize your chart based on your personal setting. There are five date markers
 Today: To mark today's date on gantt chart (blue border color surrounding the area below corresponding date).
 Holiday: To mark holiday's date on gantt chart (Red color for non working dates within a week, orange color for national/company holidays).
 Leave: To mark employee leave's date on gantt chart (Dark violet solid color on corresponding leave dates).
 Start/End: To mark the beginning and the end of one task period (Black solid color in the beginning or end of any task period).
 Passing Days: To view the progress and mark the number of days that has been passed from the beginning of any tasks until today's date (Blue solid color on corresponding dates).
Flexible Project Display Period with Scrolling Function
You can select project plan frame preference to be displayed and printed in Excel, and you can visually scroll the plan weekly or daily.
Task and Remaining Days Alert
With this feature, any project managers can be reminded on how many parallel tasks in the same day that can be carry on by his/her teams and on how many days left to complete their projects.